## Main
Oracle Applications Release11i (11.5.4)
Upgrade Assistant Spreadsheet
The R11i Upgrade Spreadsheet is a tool that will assist you in planning an Oracle Applications upgrade to Release 11i. This spreadsheet
is to be used in conjunction with the Upgrading Oracle Applications, Release 11i manual. When performing a test upgrade of your
current system, you can use this spreadsheet to enter the start and end times of any upgrade step. The total time for the step as well as the
total time for the upgrade and the time for the critical downtime will automatically be calculated. The timing statistics gathered for the
test upgrade can be used as a benchmark for subsequent test upgrades and the production upgrade.
All estimated and actual time calculations will be carried over to this Main page. The Estimated Time represents the time of the current
upgrade while the Actual Time represents the benchmark from a prior or test upgrade. The time for AutoUpgrade represents the total
running time of AutoUpgrade.
Click on the Main Menu button at the top of this page to access the Main menu dialog box. Within this dialog box select the category,
product family, and release you are upgrading from to see the list of upgrade steps pertinent to your upgrade. You can return to this Main
page from any of the other pages by clicking on the To Main Page button in the upper left corner.
For detailed instructions on how to use this spreadsheet, click on the readme button on the upper right hand corner of this page.
Always check Oracle MetaLink for the most up-to-date information.
Time by Category
|  | Estimated Time | Actual Time
|  | h:mm | h:mm
| Category 1 | 0:00 | 0:00 | Crucial Downtime |  | Total Upgrade Time
| Category 2 | 0:00 | 0:00 | Estimated Time | Actual Time | Estimated Time | Actual Time
| Category 3 | 0:00 | 0:00 | h:mm | h:mm | h:mm | h:mm
| AutoUpgrade | 0:00 | 0:00 | 0:00 | 0:00 | 0:00 | 0:00
| Category 4 | 0:00 | 0:00
| Category 5 | 0:00 | 0:00
| Category 6 | 0:00 | 0:00
| Custom | 0:00 | 0:00
AutoUpgrade
| Downtime | 0:00 | 0:00
Main Menu
Readme

## Category 1
|  |  | Format = MM/DD/YY h:mm (24 hour format) |  |  | Do not use the drop down filters. See Readme for more information.
Products | Category 1 Steps | Upgrade from | Start Time | End Time | Total Time | Actual Time | Performed | Notes |  | Total time |  |  | Actual time
| Before You Receive the Software | Release |  |  |  | from Test Upg | by |  |  | hour | minutes |  | hour | minutes
Database Upgrade Steps |  | 10.7, 11.0 | [6 empty] | db
Database Upgrade Tasks |  | 10.7, 11.0 | [6 empty] | db
Step 1 | Back up the Oracle Applications database (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 2 | Maintain Multilingual tables (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 3 | Verify operating system login (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 4 | Rename custom database objects with Applications prefixes (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 5 | Migrate or upgrade to Oracle8i Enterprise Edition (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 6 | Back up Oracle Applications and customizations (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Applications Technology Products |  | 10.7, 11.0 | [6 empty] | atg | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
System Administration Tasks |  | 10.7, 11.0 | [6 empty] | atg | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Verify ORACLE schemas (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Determine attachment file upload directory (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Review current user responsibilities (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | DB | 0 | 0 | 0:00 | DB
Step 4 | Preserve CUSTOM library (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Application Object Library Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Transition custom forms to Oracle Forms 6i (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Oracle Alert Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Run the Purge Alert and Action Set Checks alert (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Financials Product Family |  | 10.7, 11.0 | [6 empty] | fin | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Cash Management Tasks |  | 10.7, 11.0 | [6 empty] | fin | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Back up customized Reconciliation Open Interface objects (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Oracle Payables Tasks |  | 10.7, 11.0 | [6 empty] | fin | [7 empty] | 0 | convert to time |  |  | 0 | convert to time
Step 1 | Complete outstanding payment batches (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | ATG | 0 | 0 | 0:00
Oracle Projects Tasks |  | 10.7, 11.0 | [6 empty] | fin | [13 empty] | ATG
Step 1 | Complete transfer and tieback of cost, revenue, and invoices (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Clear the Transaction Interface table (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Transfer asset lines and post mass additions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 4 | Upgrade to the new summarization model (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Receivables Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Rename custom tax structure (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Save custom tax vendor extension views (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Verify realized gains, realized losses, and rounding accounts (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 4 | Migrate customers as persons (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Country-specific Financials Product Family |  | 10.7, 11.0 | [6 empty] | loc | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Financials for the Americas Tasks |  | 10.7, 11.0 | [6 empty] | loc | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Record the value of the JL: Inflation Ratio Precision profile option (required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Import outstanding bank collection documents (required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Restore all archived technical appraisals and adjustments (recommended) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Financials | 0 | 0 | 0:00 | Financials
Step 4 | Print all completed transactions (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
HRMS Product Family |  | 10.7, 11.0 | [6 empty] | hr | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Human Resources Tasks |  | 10.7, 11.0 | [6 empty] | hr | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Update custom code after removing obsolete synonyms (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Update custom reports after dropping HRV and OTV views (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Check location of customized script for Salary Proposal view (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Localizations | 0 | 0 | 0:00 | Localizations
Step 4 | Update custom code for positions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0
Step 5 | Update user-defined FastFormula definitions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0
Step 6 | Update Vertex geocodes data (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0
Oracle Payroll (U.S.) Tasks |  | 10.7, 11.0 | [6 empty] | hr
Step 1 | Update custom code for U.S. tax information (W4) changes (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0
Manufacturing and Distribution Product Family |  | 10.7, 11.0 | [6 empty] | man | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Inventory/Cost Management/Work in Process Tasks |  | 10.7, 11.0 | [6 empty] | man | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Close discrete jobs and purge unneeded data – WIP (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Public Sector |  | 10.7, 11.0 | [6 empty] | ps | [7 empty] | 0 | convert to time |  |  | 0 | convert to time
Oracle Labor Distribution Tasks |  | 10.7, 11.0 | [6 empty] | ps | [6 empty] | 0 | 0 | 0:00 | HRMS | 0 | 0 | 0:00 | HRMS
Step 1 | Ensure that transactions are summarized and transferred (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
|  | 10.7, 11.0 | SubTotal DB Steps |  | 0:00 | 0:00 |  |  | db | 0 | 0 | Total | 0 | 0 | Total | 0 | 0 | Total |  | 0 | 0 | Total |  | 0 | 0 | Total |  | 0 | 0 | Total
|  | 10.7, 11.0 | SubTotal ATG Steps |  | 0:00 | 0:00 |  |  | atg |  | 0 | minutes to hour |  | 0 | minutes to hour |  | 0 | minutes to hour |  |  | 0 | minutes to hour |  |  | 0 | minutes to hour |  |  | 0 | minutes to hour
|  | 10.7, 11.0 | SubTotal Financials Steps |  | 0:00 | 0:00 |  |  | fin | 0 |  | add h to hours | 0 |  | add h to hours | 0 |  | add h to hours |  | 0 |  | add h to hours |  | 0 |  | add h to hours |  | 0 |  | add h to hours
|  | 10.7, 11.0 | SubTotal Localizations Steps |  | 0:00 | 0:00 |  |  | loc |  | 0 | convert to time |  | 0 | convert to time |  | 0 | convert to time |  |  | 0 | convert to time |  |  | 0 | convert to time |  |  | 0 | convert to time
|  | 10.7, 11.0 | SubTotal HRMS Steps |  | 0:00 | 0:00 |  |  | hr | 0 | 0 | Total hour and minutes | 0 | 0 | Total hour and minutes | 0 | 0 | 0:00 | Manufacturing | 0 | 0 | 0:00 | Manufacturing | 0 | 0 | 0:00 | Public Sector | 0 | 0 | 0:00 | Public Sector
|  | 10.7, 11.0 | SubTotal Manufacturing Steps |  | 0:00 | 0:00 |  |  | man
|  | 10.7, 11.0 | SubTotal Public Sector Steps |  | 0:00 | 0:00 |  |  | ps
To Main Page
Verify

## Category 2
|  |  | Format = MM/DD/YY h:mm (24 hour format) |  |  | Do not use the drop down filters. See Readme for more information.
Products | Category 2 Steps | Upgrade from | Start Time | End Time | Total Time | Actual Time | Performed | Notes |  | Total time |  |  | Actual time
| After You Receive the Software | Release |  |  |  | from Test Upg | by |  |  | hour | minutes |  | hour | minutes
Environment Preparation Tasks |  | 10.7, 11.0 | [6 empty] | db
| Run Rapid Install (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
| Apply consolidated upgrade patches (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  |  | 0 | 0 |  | 0 | 0
| Export environment variables and add custom settings (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Database Upgrade Steps |  | 10.7, 11.0 | [6 empty] | db
Database Upgrade Tasks |  | 10.7, 11.0 | [6 empty] | db
Step 1 | Validate APPS schema(s) (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 2 | Set up tablespaces (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 3 | Drop custom schemas that match APPS% (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 4 | Verify custom index privileges (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 5 | Drop conflicting custom public synonyms (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Applications Technology Products |  | 10.7, 11.0 | [6 empty] | atg | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle System Administration Tasks |  | 10.7, 11.0 | [6 empty] | atg | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Delete unsuccessful login data (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Restrict access to administration directory all servers except database (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Purge old concurrent requests (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | DB | 0 | 0 | 0:00 | DB
Oracle FlexBuilder/Account Generator Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Indicate use of FlexBuilder process for Account Generator (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Financials Product Family |  | 10.7, 11.0 | [6 empty] | fin | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle General Ledger Tasks |  | 10.7, 11.0 | [6 empty] | fin | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Review daily rates (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Revise custom programs that automatically load daily rates (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Global Accounting Engine Tasks |  | 10.7, 11.0 | [6 empty] | fin | [6 empty] | 0 | 0 | 0:00 | ATG | 0 | 0 | 0:00 | ATG
Step 1 | Update accounting data model (required) | 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Ensure that all transactions are translated (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Calculate balances (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 4 | Close all accounting periods (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Payables Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Update supplier and supplier site bank data for multiple supplier banks (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Choose payment method for future dated payments (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Enable recoverable tax option (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Projects Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Correct the week ending date and month ending date for summarization data for multilingual support (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Correct excess revenue amounts data for hard limit funded agreements (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Correct excess revenue accrued for non-adjusting negative amount expenditure items (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 4 | Correct credit memo invoice dates (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 5 | Correct bill amount data stored on revenue distributions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 6 | Correct billing hold data on reversing items (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 7 | Correct billable flag data for reversing items (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 8 | Run data fix scripts (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Purchasing Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Clear open interface tables (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Country-specific Financials Product Family |  | 10.7, 11.0 | [6 empty] | loc | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Financials for Asia/Pacific Tasks |  | 10.7, 11.0 | [6 empty] | loc | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Record truncated lookup codes or renamed meanings in custom modules (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Move government uniform invoice information for each organization (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Move customer uniform numbers and tax registration numbers (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Financials | 0 | 0 | 0:00 | Financials
Step 4 | Move supplier uniform numbers and tax registration numbers (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 5 | Record uniform numbers for your company (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 6 | Record Canadian tax setup (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 7 | Print tax rebate and rule listings (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Oracle Financials for Europe Tasks |  | 10.7, 11.0 | [6 empty] | loc
Step 1 | Update Swedish EFT payment format information (required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 2 | Pay Danish EFT invoices (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Oracle Financials for the Americas Tasks |  | 10.7, 11.0 | [6 empty] | loc
Step 1 | Upgrade Brazilian subledgers data structure (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 2 | Identify and correct duplicate rows in JL_BR_LOOKUPS (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
HRMS Product Family |  | 10.7, 11.0 | [6 empty] | hr | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Human Resources Tasks |  | 10.7, 11.0 | [6 empty] | hr | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Update taskflow definitions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Manufacturing and Distribution Product Family |  | 10.7, 11.0 | [6 empty] | man | [7 empty] | 0 | convert to time |  |  | 0 | convert to time
Oracle e-Commerce Gateway Tasks |  | 10.7, 11.0 | [6 empty] | man | [6 empty] | 0 | 0 | 0:00 | Localizations | 0 | 0 | 0:00 | Localizations
Step 1 | Report output interface data file definitions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 | 0 | Total |  | 0 | 0 | Total
Step 2 | Report cross-reference data definitions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  |  | 0 | minutes to hour |  |  | 0 | minutes to hour
Oracle Inventory/Cost Management/Work in Process Tasks |  | 10.7, 11.0 | [6 empty] | man | [6 empty] | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 1 | Find and correct items with no primary unit of measure (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 2 | Purge unwanted transaction history - INV (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Hrms | 0 | 0 | 0:00 | Hrms
Oracle Order Management |  | 10.7, 11.0 | [6 empty] | man
Step 1 | Run Order Entry Interface programs (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 2 | Close eligible orders (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 3 | Run Order Import program (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 4 | Run Auto-create Installed Base program for Services (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 5 | Make sure orders are in a status supported by Order Management (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 6 | Close open pick slips/picking batches or open deliveries/departures (required) | 10.7 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 7 | Run the Shipping Interface programs (required) | 10.7 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 8 | Review Item Validation Org settings (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 9 | Validate inventory organization data (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 10 | Review cycles that may not be upgraded (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
|  | 10.7, 11.0 | SubTotal Rapid Install & DB Steps |  | 0:00 | 0:00 |  |  | db | 0 | 0 | Total | 0 | 0 | Total | 0 | 0 | Total |  | 0 | 0 | Total
|  | 10.7, 11.0 | SubTotal ATG Steps |  | 0:00 | 0:00 |  |  | atg |  | 0 | minutes to hour |  | 0 | minutes to hour |  | 0 | minutes to hour |  |  | 0 | minutes to hour
|  | 10.7, 11.0 | SubTotal Financials Steps |  | 0:00 | 0:00 |  |  | fin | 0 |  | add h to hours | 0 |  | add h to hours | 0 |  | add h to hours |  | 0 |  | add h to hours
|  | 10.7, 11.0 | SubTotal Localizations Steps |  | 0:00 | 0:00 |  |  | loc |  | 0 | convert to time |  | 0 | convert to time |  | 0 | convert to time |  |  | 0 | convert to time
|  | 10.7, 11.0 | SubTotal HRMS Steps |  | 0:00 | 0:00 |  |  | hr | 0 | 0 | Total hour and minutes | 0 | 0 | Total hour and minutes | 0 | 0 | 0:00 | Manufacturing | 0 | 0 | 0:00 | Manufacturing
|  | 10.7, 11.0 | SubTotal Manufacturing Steps |  | 0:00 | 0:00 |  |  | man
To Main Page
Verify

## Category 3
|  |  | Format = MM/DD/YY h:mm (24 hour format) |  |  | Do not use the drop down filters. See Readme for more information.
Products | Category 3 Stpes | Upgrade from | Start Time | End Time | Total Time | Actual Time | Performed | Notes |  | Total time |  |  | Actual time
| Performing the Upgrade | Release |  |  |  | from Test Upg | by |  |  | hour | minutes |  | hour | minutes
Applications Technology Products |  | 10.7, 11.0 | [6 empty] | atg
Oracle Alert Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Drop event alert triggers in custom schemas (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Oracle Common Modules Task |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Delete all AK data for Production 16 Global Demo databases (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 2 | Fix invalid AK data in non-Global Demo databases (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Oracle Workflow Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Update protection and customization levels of seeded item types (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
System Administration Tasks (Performed after all product specific Category 3 steps and before the Category 3 database steps) |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Identify potential ORACLE schema conflicts (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 2 | Enable SYSADMIN user and password (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 3 | Disable AOL Audit Trail feature (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Financials Product Family |  | 10.7, 11.0 | [6 empty] | fin | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Payables Tasks |  | 10.7, 11.0 | [6 empty] | fin | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Update existing payment records (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Determine exchange rates (MRC) (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Import and purge Payables Open Interface invoices (required) | 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | ATG | 0 | 0 | 0:00 | ATG
Step 4 | Import and purge Invoice Import Interface expense reports and invoices (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 5 | Transfer all data to General Ledger (MRC) (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Projects Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Submit and obtain approval for all timecards entered in PTE or Project Time and Expense (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Correct excess revenue accrued for negative amount events (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Back up custom client extension packages and views (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Receivables Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Drop tax vendor synonyms (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Diagnose and correct pre-existing database problems (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Country-specific Financials Product Family |  | 10.7, 11.0 | [6 empty] | loc | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Common Countries Financials Tasks |  | 10.7, 11.0 | [6 empty] | loc | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Partition EFT system formats information by operating unit (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
HRMS Product Family |  | 10.7, 11.0 | [6 empty] | hr | [7 empty] | 0 | convert to time |  |  | 0 | convert to time
Oracle Payroll (U.S.) Tasks |  | 10.7, 11.0 | [6 empty] | hr | [6 empty] | 0 | 0 | 0:00 | Financials | 0 | 0 | 0:00 | Financials
Step 1 | Remove triggers specific to PayMIX (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 |  | 0 | 0 | Total |  | 0 | 0 | Total
Manufacturing and Distribution Product Family |  | 10.7, 11.0 | [6 empty] | man | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Oracle Inventory/Cost Management/Work in Process Tasks |  | 10.7, 11.0 | [6 empty] | man | [6 empty] | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 1 | Complete physical inventories in process - INV (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 2 | Process data in temporary and interface tables - INV (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Localizations | 0 | 0 | 0:00 | Localizations
Step 3 | Verify that no uncosted transactions exist - Standard and Average Costing (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 | 0 | Total |  | 0 | 0 | Total
Step 4 | Run inventory valuation reports - INV (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  |  | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 5 | Run WIP Value report- Standard and Average Costing (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 6 | Close all accounting periods - Standard and Average Costing (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Oracle Order Management |  | 10.7, 11.0 | [6 empty] | man | [6 empty] | 0 | 0 | 0:00 | HRMS | 0 | 0 | 0:00 | HRMS
Step 1 | Repeat Category 2 steps 1 – 10 (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Oracle Purchasing Tasks |  | 10.7, 11.0 | [6 empty] | man
Step 1 | Modify default MRP profile options (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 2 | Drop ICX index (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Public Sector |  | 10.7, 11.0 | [6 empty] | ps | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Grants Accounting Tasks |  | 10.7, 11.0 | [6 empty] | ps | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Run costing and funds check procedures (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Run the update awards summary (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Rename the Grants Accounting tables (required) | 10.7 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Manufacturing | 0 | 0 | 0:00 | Manufacturing
Step 4 | Run data correction script (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
Oracle U.S. Federal Financials Tasks |  | 10.7, 11.0 | [6 empty] | ps
Step 1 | Drop obsolete seed data (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
Step 2 | Drop obsolete database objects (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
Step 3 | Upgrade menus (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  | 0 | 0 | Total |  | 0 | 0 | Total
Step 4 | Drop indexes (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  |  | 0 | minutes to hour |  |  | 0 | minutes to hour
Database Upgrade Steps |  | 10.7, 11.0 | [6 empty] | db | [6 empty] | 0 |  | add h to hours |  | 0 |  | add h to hours
Database Upgrade Tasks |  | 10.7, 11.0 | [6 empty] | db | [7 empty] | 0 | convert to time |  |  | 0 | convert to time
Step 1 | Shut down all applications listeners and concurrent managers (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Public Sector | 0 | 0 | 0:00 | Public Sector
Step 2 | Migrate or upgrade to Oracle8i Enterprise Edition (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 3 | Set up Net8 - database server (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 4 | Run preparatory scripts - database server (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 5 | Gather database statistics for CBO. | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 6 | Install database objects for the Oracle HTTP server (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 7 | Gather database information (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 8 | Check SQL*Plus options (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 9 | Verify rollback segment sizing (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 10 | Turn off automatic archive logging (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 11 | Disable custom triggers, constraints, and indexes (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 12 | Run preparatory scripts – admin server (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 13 | Back up the Oracle Applications database (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 14 | Complete database upgrade steps for NLS databases (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
|  | 10.7, 11.0 | SubTotal DB Steps |  | 0:00 | 0:00 |  |  | db | 0 | 0 | Total | 0 | 0 | Total | 0 | 0 | Total |  | 0 | 0 | Total
|  | 10.7, 11.0 | SubTotal ATG Steps |  | 0:00 | 0:00 |  |  | atg |  | 0 | minutes to hour |  | 0 | minutes to hour |  | 0 | minutes to hour |  |  | 0 | minutes to hour
|  | 10.7, 11.0 | SubTotal Financials Steps |  | 0:00 | 0:00 |  |  | fin | 0 |  | add h to hours | 0 |  | add h to hours | 0 |  | add h to hours |  | 0 |  | add h to hours | DB
|  | 10.7, 11.0 | SubTotal Localizations Steps |  | 0:00 | 0:00 |  |  | loc |  | 0 | convert to time |  | 0 | convert to time |  | 0 | convert to time |  |  | 0 | convert to time
|  | 10.7, 11.0 | SubTotal HRMS Steps |  | 0:00 | 0:00 |  |  | hr | 0 | 0 | Total hour and minutes | 0 | 0 | Total hour and minutes | 0 | 0 | 0:00 | DB | 0 | 0 | 0:00
|  | 10.7, 11.0 | SubTotal Manufacturing Steps |  | 0:00 | 0:00 |  |  | man
|  | 10.7, 11.0 | SubTotal Public Sector Steps |  | 0:00 | 0:00 |  |  | ps
To Main Page
Verify

## AutoUpgrade
| AutoUpgrade | Start Time | End Time | Total Time | Actual Time | Performed by | Notes | Total time Runtime |  | Total time Downtime |  |  | Actual time Runtime |  | Actual time Downtime
| Runtime and Downtime | Format = MM/DD/YY h:mm (24 hour format) |  |  | from Test Upg |  |  | hour | minutes | hour | minutes |  | hour | minutes | hour | minutes
AutoUpgrade
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
| Runtime |  |  | 0:00 |  |  |  | 0 | 0 |  |  |  | 0 | 0
| Downtime |  |  | 0:00 | [5 empty] | 0 | 0 |  |  |  | 0 | 0
|  |  |  | 0:00 |  |  |  | 0 | 0 | 0 | 0 | Total | 0 | 0 | 0 | 0 | Total
[9 empty] | 0 |  | 0 | minutes to hour |  | 0 |  | 0 | minutes to hour
[8 empty] | 0 |  | 0 |  | add h to hours | 0 |  | 0 |  | add h to hours
[9 empty] | 0 |  | 0 | convert to time |  | 0 |  | 0 | convert to time
[8 empty] | 0 | 0 | 0 | 0 | Total hour and minutes | 0 | 0 | 0 | 0 | Total hour and minutes
To Main Page

## Category 4
|  |  | Format = MM/DD/YY h:mm (24 hour format) |  |  | Do not use the drop down filters. See Readme for more information.
Products | Category 4 Steps | Upgrade from | Start Time | End Time | Total Time | Actual Time | Performed | Notes |  | Total time |  |  | Actual time
| Before Using Oracle Applications | Release |  |  |  | from Test Upg | by |  |  | hour | minutes |  | hour | minutes
Database Upgrade Steps |  | 10.7, 11.0 | [6 empty] | db
Database Upgrade Tasks |  | 10.7, 11.0 | [6 empty] | db
Step 1 | Update Database to Current Applications Release Level (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 2 | Install online help (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 3 | Install NLS translated software (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 4 | Run Rapid Install to configure and start server processes (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 5 | Configure Applications client software (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 6 | Reset ORACLE schema passwords (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 7 | Gather database statistics for CBO (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 8 | Reapply product customizations to environment and files (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 9 | Set rollback segments for normal use (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 10 | Install XML Parser for PL/SQL (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 11 | Validate and compile APPS schema(s) (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 12 | Integrate custom objects and schemas (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 13 | Re-enable custom triggers, constraints, and indexes (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 14 | Back up Oracle Applications (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Upgrading Multiple Reporting Currencies (MRC) |  | 10.7, 11.0 | [6 empty] | db
Multiple Reporting Currencies Tasks |  | 10.7, 11.0 | [6 empty] | db
Step 1 | Validate and compile APPS schema(s) (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 2 | Maintain MRC schema(s) (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Step 3 | Verify your MRC installation (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0
Applications Technology Products |  | 10.7, 11.0 | [6 empty] | atg | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
System Administration Tasks |  | 10.7, 11.0 | [6 empty] | atg | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Fix flexfields cross-validation rules (required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Set profile options (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Clone Date and DateTime value sets (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | DB | 0 | 0 | 0:00 | DB
Step 4 | Upgrade flexfield date and number data (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 5 | Set up electronic mail for use by concurrent managers (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 6 | Reconnect spawned concurrent programs (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 7 | Update/verify custom responsibilities (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 8 | Copy and re-customize previously modified scripts or reports (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 9 | Migrate your CUSTOM library (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 10 | Copy existing custom start scripts (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 11 | Restrict access to concurrent processing servers (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 13 | Load attachment files into database (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Oracle FlexBuilder/Account Generator Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Complete installation steps for Oracle Workflow (required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 2 | Complete installation steps for Oracle Workflow Builder (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 3 | Update Account Generator process (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 4 | Associate FlexBuilder rules for Accounting Flexfield structure and Workflow item type (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Country-specific Financials Product Family |  | 10.7, 11.0 | [6 empty] | loc | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Financials for Asia/Pacific Tasks |  | 10.7, 11.0 | [6 empty] | loc | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Modify truncated lookup codes or renamed meanings in custom modules (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Oracle Financials Common Country Features Tasks |  | 10.7, 11.0 | [6 empty] | loc | [7 empty] | 0 | convert to time |  |  | 0 | convert to time
Step 1 | Upgrade descriptive flexfield dates to use the new AOL date validation (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | ATG | 0 | 0 | 0:00 | ATG
Manufacturing and Distribution Product Family |  | 10.7, 11.0 | [6 empty] | man | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle e-Commerce Gateway Tasks |  | 10.7, 11.0 | [6 empty] | man | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Report output interface data file definitions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Report cross-reference data definitions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Public Sector |  | 10.7, 11.0 | [6 empty] | ps | [6 empty] | 0 | 0 | 0:00 | Localizations | 0 | 0 | 0:00 | Localizations
Oracle Grants Accounting Tasks |  | 10.7, 11.0 | [6 empty] | ps | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Step 1 | Verify new profiles (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  |  | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 2 | Run migration driver (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 3 | Verify billing amounts (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 4 | Verify award balances (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Manufacturing | 0 | 0 | 0:00 | Manufacturing
Environment Preparation Tasks |  | 10.7, 11.0 | [6 empty] | db | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Step 1 | Verify application server DAD (required) | 11.0 |  |  | 0:00 |  |  |  | db | 0 | 0 |  | 0 | 0 |  |  | 0 | minutes to hour |  |  | 0 | minutes to hour
|  | 10.7, 11.0 | SubTotal DB, MRC, & Env. Steps |  | 0:00 | 0:00 |  |  | db | 0 | 0 | Total | 0 | 0 | Total | 0 |  | add h to hours |  | 0 |  | add h to hours
|  | 10.7, 11.0 | SubTotal ATG Steps |  | 0:00 | 0:00 |  |  | atg |  | 0 | minutes to hour |  | 0 | minutes to hour |  | 0 | convert to time |  |  | 0 | convert to time
|  | 10.7, 11.0 | SubTotal Localizations Steps |  | 0:00 | 0:00 |  |  | loc | 0 |  | add h to hours | 0 |  | add h to hours | 0 | 0 | 0:00 | Public Sector | 0 | 0 | 0:00 | Public Sector
|  | 10.7, 11.0 | SubTotal Manufacturing Steps |  | 0:00 | 0:00 |  |  | man |  | 0 | convert to time |  | 0 | convert to time
|  | 10.7, 11.0 | SubTotal Public Sector Steps |  | 0:00 | 0:00 |  |  | ps | 0 | 0 | Total hour and minutes | 0 | 0 | Total hour and minutes
To Main Page
Verify

## Category 5
|  |  | Format = MM/DD/YY h:mm (24 hour format) |  |  | Do not use the drop down filters. See Readme for more information.
Products | Category 5 Steps | Upgrade from | Start Time | End Time | Total Time | Actual Time | Performed | Notes |  | Total time |  |  | Actual time
| Before Using Your Products | Release |  |  |  | from Test Upg | by |  |  | hour | minutes |  | hour | minutes
Financials Product Family |  | 10.7, 11.0 | [6 empty] | fin
Oracle General Ledger Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Migrate conflicting daily rates (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Global Accounting Engine Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Migrate existing date and non-integer data (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Update existing balances and accounting lines (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Migrate obsolete event types and document statuses (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 4 | Update the Transfer to GL posted flag (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 5 | Populate tax information for accounting lines (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Payables Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Remodify payment formats (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Set up prepayment payment terms (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Projects Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Review organization hierarchies and uses of organizations (required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Update project status values (required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Update customized billing extensions (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 4 | Review and update billing cycle names (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 5 | Convert custom overtime calculation program to PL/SQL (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 6 | Populate billing title for employee assignments (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 7 | Set up the invoice rounding account (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 8 | Add new parameters to customized invoice-related client extensions (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 9 | Add new parameters to customized transaction control extension (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 10 | Add new currencies and non-recoverable tax amounts to commitment views (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 11 | Update custom code that populates the Transaction Interface table (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 12 | Reinstall customized client extension packages and views (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 13 | Correct FIFO marking of expenditure items (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 14 | Update the currency and the billing and shipping addresses of draft invoices (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 15 | Drop invalidated packages (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Receivables Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Create indexes on transaction flexfield columns (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Recreate custom tax vendor extension views (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Update tax vendor descriptive flexfield information (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 4 | Create contexts and segments for new flexfields (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Country-specific Financials Product Family |  | 10.7, 11.0 | [6 empty] | loc | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Financials Common Countries Features Tasks |  | 10.7, 11.0 | [6 empty] | loc | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Update customized menus that use JG submenus (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Enable the Swift Code field in the Enter Banks window (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Oracle Financials for Asia/Pacific Tasks |  | 10.7, 11.0 | [6 empty] | loc | [6 empty] | 0 | 0 | 0:00 | Financials | 0 | 0 | 0:00 | Financials
Step 1 | Correct existing data before reporting tax information (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Oracle Financials for Europe Tasks |  | 10.7, 11.0 | [6 empty] | loc
Step 1 | Upgrade character-mode responsibilities (recommended) | 10.7 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 2 | Update customized menus that use JE submenus (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Oracle Financials for the Americas Tasks |  | 10.7, 11.0 | [6 empty] | loc
Step 1 | Set the value of the JL: Inflation Ratio Precision profile option (required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 2 | Create new lookup codes (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 3 | Set tax system options (required) | 10.7 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 4 | Update sales orders and invoices (required) | 10.7 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 5 | Add warehouse name information (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 6 | Associate tax information for each inventory organization location (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 7 | Associate tax groups and tax categories (required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 8 | Cancel and re-enter all unapproved and unposted invoices (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 9 | Archive restored technical appraisals (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
HRMS Product Family |  | 10.7, 11.0 | [6 empty] | hr | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Human Resources/Payroll Tasks (U.S., U.K., and Japan) |  | 10.7, 11.0 | [6 empty] | hr | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Select legislative and college data with DataInstall (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Run the global legislation driver (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Run the exchange rate migration script (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Localizations | 0 | 0 | 0:00
Step 4 | Associate a set of books with your organizational payment method (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 | [8 empty] | Localizations
Manufacturing and Distribution Product Family |  | 10.7, 11.0 | [6 empty] | man | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Inventory/Cost Management/Work in Process Tasks |  | 10.7, 11.0 | [6 empty] | man | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Review and correct organization default accounts - INV (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Verify totals in inventory valuation reports - INV (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Verify balances in WIP Value reports (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | HRMS | 0 | 0 | 0:00 | HRMS
Step 4 | Define default material subelement - Average Costing (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 5 | Define Average Rates cost type - Average Costing (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Oracle Master Scheduling/MRP and Supply Chain Planning Tasks |  | 10.7, 11.0 | [6 empty] | man
Step 1 | Start the Planning Manager (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Oracle Order Management |  | 10.7, 11.0 | [6 empty] | man
Step 1 | Document upgrade errors (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 2 | Create OM profile option for the Cycles to Workflow upgrade (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 3 | Set up responsibilities for order creation/manipulation (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 4 | Review upgraded transaction types (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 5 | Set up processing constraints (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 6 | Set up flexfield definitions (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 7 | Review seeded attributes and their sequences (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 8 | Set up pricing profiles (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 9 | Define pick slip grouping rules (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 10 | Define release sequence rules (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 11 | Define shipping parameters for inventory organizations (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 12 | Define ship methods lookups and map to freight carriers (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 13 | Set up shipping execution profiles and menus (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Oracle Purchasing Tasks |  | 10.7, 11.0 | [6 empty] | man
Step 1 | Activate transaction managers for MultiOrg (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 2 | Upgrade notifications (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 3 | Set MRP profile options (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 4 | Verify and modify sourcing rules (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 5 | Verify date formats (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Step 6 | Verify RMA upgrade (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0
Public Sector |  | 10.7, 11.0 | [6 empty] | ps | [6 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Labor Distribution Tasks |  | 10.7, 11.0 | [6 empty] | ps | [7 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Upgrade Labor Distribution and remove obsolete objects (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
Oracle U.S. Federal Financials Tasks |  | 10.7, 11.0 | [6 empty] | ps | [7 empty] | 0 | convert to time |  |  | 0 | convert to time
Step 1 | Migrate data to new tables (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0:00 | Manufacturing | 0 | 0 | 0:00
Step 2 | Load seed data (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 | [8 empty] | Manufacturing
|  | 10.7, 11.0 | SubTotal Financials Steps |  | 0:00 | 0:00 |  |  | fin | 0 | 0 | Total | 0 | 0 | Total | 0 | 0 | Total |  | 0 | 0 | Total
|  | 10.7, 11.0 | SubTotal Localizations Steps |  | 0:00 | 0:00 |  |  | loc |  | 0 | minutes to hour |  | 0 | minutes to hour |  | 0 | minutes to hour |  |  | 0 | minutes to hour
|  | 10.7, 11.0 | SubTotal HRMS Steps |  | 0:00 | 0:00 |  |  | hr | 0 |  | add h to hours | 0 |  | add h to hours | 0 |  | add h to hours |  | 0 |  | add h to hours
|  | 10.7, 11.0 | SubTotal Manufacturing Steps |  | 0:00 | 0:00 |  |  | man |  | 0 | convert value to time value |  | 0 | convert value to time value |  | 0 | convert to time |  |  | 0 | convert to time
|  | 10.7, 11.0 | SubTotal Public Sector Steps |  | 0:00 | 0:00 |  |  | ps | 0 | 0 | Total hour and minutes | 0 | 0 | Total hour and minutes | 0 | 0 | 0:00 | Public Sector | 0 | 0 | 0:00
[6 empty] | . | [16 empty] | Public Sector
To Main Page
Verify

## Category 6
|  |  | Format = MM/DD/YY h:mm (24 hour format) |  |  | Do not use the drop down filters. See Readme for more information.
Products | Category 6 Steps | Upgrade from | Start Time | End Time | Total Time | Actual Time | Performed | Notes |  | Total time |  |  | Actual time
| Before Using Product Features | Release |  |  |  | from Test Upg | by |  |  | hour | minutes |  | hour | minutes
Applications Technology Products |  | 10.7, 11.0 | [6 empty] | atg
System Administration Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Set up report security groups (conditionally recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 2 | Upgrade accounting calendar (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Application Object Library Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Update custom code using flexfield values in FND_LOOKUPS (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 2 | Update custom calls to FND_DESCR_FLEX_CONTEXT_TL (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 3 | Rename the /srw directory to /reports for custom applications (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 4 | Copy custom forms libraries to AU_TOP (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 5 | Copy custom .fmb files to AU_TOP (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 6 | Convert character-mode messages to GUI for custom applications (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 7 | Regenerate, recompile, and re-link custom concurrent program libraries (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Oracle Alert Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Associate organization names to pre-existing custom Alert definitions (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Step 2 | Re-create event alert triggers (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Oracle Common Modules Tasks |  | 10.7, 11.0 | [6 empty] | atg
Step 1 | Restore and back up custom data for non-Global Demo databases (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | atg | 0 | 0 |  | 0 | 0
Financials Product Family |  | 10.7, 11.0 | [6 empty] | fin | [5 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Cash Management Tasks |  | 10.7, 11.0 | [6 empty] | fin | [6 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Reinstall customized Reconciliation Open Interface objects (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0 | 0 |  | add h to hours |  | 0 |  | add h to hours
Oracle General Ledger Tasks |  | 10.7, 11.0 | [6 empty] | fin | [6 empty] | 0 | convert to time |  |  | 0 | convert to time
Step 1 | Preserve GL account combinations affected by the Segment Value Inheritance program (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0 | 0 | 0 | 0:00 | ATG | 0 | 0 | 0:00 | ATG
Step 2 | Ensure that account segment values use correct account type(conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Review period rates (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 4 | Define Owners Equity Translation Rule profile option(conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 5 | Define income statement accounts revaluation profile option (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 6 | Review AutoPost criteria (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 7 | Define GIS conversion rates and rate types (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 8 | Verify program submission parameters for mass funds check/reservation (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 9 | Set function security for journal posting and reversing functions (recommended) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 10 | Define Daily Rates profile option (recommended) | 10.7 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 11 | Set up intercompany balancing (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Payables Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Set up Offset taxes (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Set up the future dated payment account (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 3 | Set up recoverable taxes (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 4 | Link GL records and AP records (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Projects Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Implement Self-Service Time (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Implement cross charge (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Oracle Receivables Tasks |  | 10.7, 11.0 | [6 empty] | fin
Step 1 | Define GL tax assignments for Natural Account tax codes (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Step 2 | Link GL and AR records (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | fin | 0 | 0 |  | 0 | 0
Country-specific Financials Product Family |  | 10.7, 11.0 | [6 empty] | loc | [5 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Financials for Asia/Pacific Tasks |  | 10.7, 11.0 | [6 empty] | loc | [6 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Enter uniform numbers for your company – Taiwan (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 2 | Enter GST registration information – Singapore (required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Update tax types (recommended) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 | 0 | 0 | 0:00 | Financials | 0 | 0 | 0:00
Step 4 | Modify existing globalization flexfields in Payables (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0 | [7 empty] | Financials
Step 5 | Update Thai Payables tax codes (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 6 | Update Thai Payables globalization flexfield attributes (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 7 | Modify the attribute set for the Thai Output Tax Summary report (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Oracle Common Countries Financials Tasks |  | 10.7, 11.0 | [6 empty] | loc
Step 1 | Set up Appreciation QuickCode (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 2 | Upgrade Appreciation transactions (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 3 | Assign request groups to your responsibilities (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Oracle Financials for Europe Tasks |  | 10.7, 11.0 | [6 empty] | loc
Step 1 | Update Polish and Turkish journal line sequence numbers (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 2 | Update Spanish globalization flexfield contexts (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 3 | Update Danish EFT invoices to use EDI flexfield (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 4 | Recreate French income tax types (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 5 | Update French deductible VAT invoices (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 6 | Update Italian VAT transactions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 7 | Create Italian inventory tax types (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 8 | Update taxable amounts for custom bills and self invoices (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 9 | Update Hungarian VAT transactions (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 10 | Enable the Additional Information for Hungary globalization flexfield (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Step 11 | Enable the Tax Code field in the Receipts window (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
Oracle Financials for the Americas Tasks |  | 10.7, 11.0 | [6 empty] | loc
Step 1 | Update Colombian journal line third party information (conditionally required) | 11.0 |  |  | 0:00 |  |  |  | loc | 0 | 0 |  | 0 | 0
HRMS Product Family |  | 10.7, 11.0 | [6 empty] | hr | [5 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Human Resources Tasks |  | 10.7, 11.0 | [6 empty] | hr | [6 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Recreate custom Salary Proposal view (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 | 0 |  | add h to hours |  | 0 |  | add h to hours | Localizations
Step 2 | Drop obsolete Oracle users (recommended) | 10.7 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0 |  | 0 | convert to time |  |  | 0 | convert to time
Oracle Payroll (U.S.) Tasks |  | 10.7, 11.0 | [6 empty] | hr | [5 empty] | 0 | 0 | 0:00 | Localizations | 0 | 0 | 0:00
Step 1 | Check for invalid U.S. address information (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | hr | 0 | 0 |  | 0 | 0
Manufacturing and Distribution Product Family |  | 10.7, 11.0 | [6 empty] | man | [5 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Oracle Inventory/Cost Management/Work in Process Tasks |  | 10.7, 11.0 | [6 empty] | man | [6 empty] | 0 | minutes to hour |  |  | 0 | minutes to hour
Step 1 | Create indexes on flexfield segment columns - INV (recommended) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 | 0 |  | add h to hours |  | 0 |  | add h to hours | HRMS
Step 2 | Define Item Catalog Description profile option - INV (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 |  | 0 | convert to time |  |  | 0 | convert to time
Step 3 | Update item descriptions - INV (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | man | 0 | 0 |  | 0 | 0 | 0 | 0 | 0:00 | HRMS | 0 | 0 | 0:00
Public Sector |  | 10.7, 11.0 | [6 empty] | ps
Oracle Grants Accounting Tasks |  | 10.7, 11.0 | [6 empty] | ps | [5 empty] | 0 | 0 | Total |  | 0 | 0 | Total
Step 1 | Drop obsolete tables (optional) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  | 0 | minutes to hour |  |  | 0 | minutes to hour
Public Sector Budgeting Tasks |  | 10.7, 11.0 | [6 empty] | ps | [5 empty] | 0 |  | add h to hours |  | 0 |  | add h to hours
Step 1 | Ensure account segment values use correct account type (conditionally required) | 10.7 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 |  | 0 | convert to time |  |  | 0 | convert to time
Step 2 | Convert dates stored in character columns into canonical format (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0 | 0 | 0 | 0:00 | Manufacturing | 0 | 0 | 0:00 | Manufacturing
Step 3 | Convert real numbers stored in character columns into multiradix format (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
Step 4 | Create baseline budgets from historical worksheets for use in budget revisions for line items and positions (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
Step 5 | Enable Excel interface functionality (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
Step 6 | Enable Oracle Financial Analyzer functionality (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
Oracle U.S. Federal Financials Tasks |  | 10.7, 11.0 | [6 empty] | ps
Step 1 | Reset the profile options (conditionally required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
Step 2 | Set up holiday and non-working days (required) | 10.7, 11.0 |  |  | 0:00 |  |  |  | ps | 0 | 0 |  | 0 | 0
|  | 10.7, 11.0 | SubTotal ATG Steps |  | 0:00 | 0:00 |  |  | atg | 0 | 0 | Total | 0 | 0 | 0 | 0 | Total |  | 0 | 0 | Total
|  | 10.7, 11.0 | SubTotal Financials Steps |  | 0:00 | 0:00 |  |  | fin |  | 0 | minutes to hour |  | 0 |  | 0 | minutes to hour |  |  | 0 | minutes to hour
|  | 10.7, 11.0 | SubTotal Localizations Steps |  | 0:00 | 0:00 |  |  | loc | 0 |  | add h to hours | 0 |  | 0 |  | add h to hours |  | 0 |  | add h to hours
|  | 10.7, 11.0 | SubTotal HRMS Steps |  | 0:00 | 0:00 |  |  | hr |  | 0 | convert value to time value |  | 0 |  | 0 | convert to time |  |  | 0 | convert to time
|  | 10.7, 11.0 | SubTotal Manufacturing Steps |  | 0:00 | 0:00 |  |  | man | 0 | 0 | Total hour and minutes | 0 | 0 | 0 | 0 | 0:00 | Public Sector | 0 | 0 | 0:00 | Public Sector
|  | 10.7, 11.0 | SubTotal Public Sector Steps |  | 0:00 | 0:00 |  |  | ps
To Main Page
Verify

## Custom
Products | Custom | Start Time | End Time | Total Time | Actual Time | Performed by | Notes | Total time |  |  | Actual time
| Steps | Format = MM/DD/YY h:mm (24 hour format) |  |  | from Test Upg |  |  | hour | minutes |  | hour | minutes
Enter Your Custom Steps Here:
Step 1 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 2 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 3 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 4 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 5 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 6 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 7 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 8 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 9 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 10 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 11 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 12 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 13 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 14 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 15 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 16 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 17 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 18 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 19 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 20 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 21 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 22 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 23 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 24 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 25 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 26 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 27 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 28 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 29 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 30 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 31 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 32 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 33 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 34 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 35 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 36 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 37 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 38 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 39 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 40 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 41 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 42 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 43 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 44 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 45 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 46 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 47 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 48 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 49 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
Step 50 |  |  |  | 0:00 |  |  |  | 0 | 0 |  | 0 | 0
|  |  |  | 0:00 |  |  |  | 0 | 0 | Total | 0 | 0 | Total
[9 empty] | 0 | minutes to hour |  | 0 | minutes to hour
[8 empty] | 0 |  | add h to hours | 0 |  | add h to hours
[9 empty] | 0 | convert to time |  | 0 | convert to time
[8 empty] | 0 | 0 | Total hour and minutes | 0 | 0 | Total hour and minutes
To Main Page

## readme
Oracle11i Upgrade Assistant Spreadsheet
Release Notes, Release 11.5.4
Copyright 2000, 2001 Oracle Corporation. All Rights Reserved.
This readme contains the following sections:
1. Introduction
2. Send us your comments
3. Detailed Instructions
4. Additional Information
Introduction:
The R11i Upgrade Spreadsheet is a tool that will assist you in planning an Oracle Applications upgrade to
Release 11i. This spreadsheet is to be used in conjunction with the Upgrading Oracle Applications, Release 11i
manual. When performing a test upgrade of your current system you can use this spreadsheet to enter the start
and end times of any upgrade step. The total time for the step as well as the total time for the upgrade and the
time for the critical downtime will automatically be calculated. The timing statistics gathered for the test upgrade
can be used as a benchmark for subsequent test upgrades and the production upgrade.
The upgrade is comprised of six categories and the AutoUpgrade run. Categories 1, 2, and 3 are pre-upgrade
steps and are performed before running AutoUpgrade. Categories 4, 5, and 6 are post-upgrade steps and are
performed after a successful AutoUpgrade run. Categories 3, 4, and 5 fall in the crucial downtime period of an
upgrade. During this downtime period, your users will not be able to use Oracle Applications.
Send us your comments:
We welcome your comments and suggestions on the quality and usefulness of this spreadsheet. Your input will
help us improve the next release.
Consider the following:
- Did you find any errors?
- Is the information clearly presented?
- Do you need more information? If so, where?
- What features did you like most about this spreadsheet?
If you find errors or have any other suggestions for improvement, please indicate the sheet, feature, or
functionality (if available). You can send comments to us in the following ways:
| FAX: | 650.506.1113 Attn: Oracle Applications Release Group
postal service:
Oracle Corporation
Oracle Applications Release Group
M/S 3op4
500 Oracle Parkway
Redwood Shores, CA 94065 U.S.A
| email: | apps_relgrp_us@oracle.com
Detailed Instructions:
1. Main Page
Each time the spreadsheet is opened it will default to the Main page. The Main page contains summary time
information for the upgrade. All total calculations are carried over from the individual category sheets to this
page.
To begin using the Upgrade Assistant Spreadsheet, click on the Main Menu button in the upper right hand
corner of the Main page. This will produce the Main Menu dialog box. Within the dialog box you can select the
category, product family and the release you are upgrading from for the upgrade steps that you would like to see.
The Category selections are
|  | 1 pre-upgrade |  | = Category 1 pre-upgrade steps
|  | 2 pre-upgrade |  | = Category 2 pre-upgrade steps
|  | 3 pre-upgrade |  | = Category 3 pre-upgrade steps
|  | AutoUpgrade |  | = For the AutoUpgrade run
|  | 4 pre-upgrade |  | = Category 4 post-upgrade steps
|  | 5 pre-upgrade |  | = Category 5 post -upgrade steps
|  | 6 pre-upgrade |  | = Category 6 post -upgrade steps
|  | Custom |  | = For any custom upgrade steps
The Product Family selections are
|  | Database Upgrade Steps |  |  |  | = All database related steps
|  | Applications Technology Products |  |  |  | = All System Administration and Apps Technology products steps
|  | Financials Product Family |  |  |  | = All Financials products steps
|  | Country-specific Financials Product Family |  |  |  | = All Country-specific products steps
|  | HRMS Product Family |  |  |  | = All Human Resources Management Systems Products steps
|  | Manufacturing and Distribution Product Family |  |  |  | = All Manufac. and Distrib. products steps
|  | Public Sector Product Family |  |  |  | = All Public Sector products steps
|  | All Products |  |  |  | = Shows a list of all product upgrade steps
The Release selections are
|  | 10.7 |  | = For steps when upgrading from Release 10.7
|  | 11 |  | = For steps when upgrading form Release 11.0
|  | All Releases |  | = For all upgrade steps regardless of release upgrading from
By making your selections and clicking [ok], the spreadsheet will query the list of selected upgrade steps. The
Category and Product Family search criteria are required and a message box will notify you if either of these two
criteria are left blank.
Once the start and end times for the upgrade steps are entered into the category sheets, all estimated and actual
time calculations will be carried over to this Main page. The Estimated Time represents the time of the current
upgrade while the Actual Time represents the benchmark from a prior or test upgrade. The time for
AutoUpgrade represents the total running time. Any AutoUpgrade downtime will appear in the AutoUpgrade
Downtime section under Time by Category and will not be added to total time. The Crucial Downtime totals
represent the time for all Category 3, 4, and 5 steps and the AutoUpgrade run.
2. The Category pages
Each of the Category sheets (Category 1 - Category 6) can be accessed by clicking on the sheet tab at the bottom
or by selecting the desired category in the Main Menu dialog box.
The shaded area on these sheets should not be updated and the drop down filters at the top of the page should
not be used for manual queries. See additional information # 3 below for details on the drop down filters.
The Start Time, End Time, Actual Time, Performed By, and Notes fields can be updated on these category
sheets.
|  | Start Time |  | = Enter the time the upgrade step was started
|  | End Time |  | = Enter the time the upgrade step was completed
|  | Actual Time |  | = You copy the time from a prior upgrade here to use as a benchmark for the current upgrade
|  | Performed By |  | = Enter the name of the person performing the step
|  | Notes |  | = Enter any additional information that may be useful for subsequent upgrades
When entering the start time and end time for a step, please enter it in the format "MM/DD/YY h:mm", where h
is the hour and mm are the minutes. The time should be entered in 24 hour format (i.e. 3:00 PM = 15:00). If the
time to complete a step does not cross over into the next day, the date is not necessary. You can enter just the
time in 24 hour format. The Total Time column will be calculated based upon the start and end times you enter.
The Actual Time column can be used to paste in the total time required for the step during a test or prior
upgrade, thereby allowing you to track the progress of the current upgrade against a benchmark.
Clicking the To Main Page button in the upper left corner will take you back to the Main page of this
spreadsheet. The Verify button will provide you with information on the number of incomplete steps in the
respective category sheet. The Verify button will provide all incomplete steps regardless of whether or not they
are required for you upgrade. Therefore, if you are not performing any Financials upgrade steps, you can ignore
the message that states you have incomplete Financials steps.
3. The AutoUpgrade page
This sheet is used to enter the runtimes and downtimes of your AutoUpgrade run. This sheet can be accessed by
clicking on the sheet tab at the bottom or by selecting AutoUpgrade in the Category section of the Main Menu
dialog box. When selecting AutoUpgrade as the Category in the Main Menu dialog box, the Product Family and
Release fields can be left blank.
Runtime represents the actual running time of AutoUpgrade and Downtime represents any time AutoUpgrade
must be shut down or halts during the upgrade process.
See the Category Pages section above for an explanation of the updateable Start Time, End Time, Actual Time,
Performed By, and Notes fields and the To Main Page button.
The AD Timing report produced by AutoUpgrade provides timing information on the jobs performed by AutoUpgrade.
See the Maintaining Oracle Applications manual for additional information on this report.
4. The Custom page
The Custom page is provided for any custom upgrade steps that you may want to time. This sheet can be
accessed by clicking on the sheet tab at the bottom or by selecting Custom in the Category section of the Main
Menu dialog box. When selecting Custom as the Category in the Main Menu dialog box, the Product Family and
Release fields can be left blank.
The Custom Steps column allows you to enter a description of the custom step you are performing.
See the Category Pages section above for an explanation of the updateable Start Time, End Time, Actual Time,
Performed By, and Notes fields and the To Main Page button.
5. The Other sheets
The Index, Module1, and main_form sheets store the various functionalities of the spreadsheet. These sheets are
protected and should not require any updates or edits.
Additional Information:
1. Reset Category sheets
When you query for and display upgrade steps for a product, the steps will remain displayed until another set of
steps is queried.
e.g. Select Category = 1 pre-upgrade
Product = Financials Product Family
Release = All Releases
This will display all upgrade steps for the Financials Product Family in Category 1. Until you run a new query,
the upgrade steps for the Financials Product Family will remain displayed.
To reset the sheet so that all products are displayed, go to the main menu, select the desired category and select
All Products ( upg. from 10.7 and 11.0 ) in the product drop down box. It is not necessary to select a release.
e.g. To reset the above example select
Category = 1 pre-upgrade
Product = All Products ( upg. from 10.7 and 11.0 ).
This will cause all products and steps to be displayed on the Category 1 sheet.
2. Step numbers
When you use the Main Menu to query for a particular set of steps, you may notice that the resulting steps
are not numbered sequentially.
e.g. Select Category = 1 pre-upgrade, Product = Applications Technology Products, and Release = 11.0. The
System Administration Task will show the following steps:
step 1:...
step 2:...
step 3:...
step 5:..
This is normal functionality for the Timing Spreadsheet, as the step numbers in the spreadsheet coordinate with
the step numbers in the Upgrading Oracle Applications manual. The missing step numbers have been filtered
out as they do not apply to your upgrade.
3. Drop down filters
The buttons with down arrows that appear on the second row of each of the Category sheets are used by the
spreadsheet's built in macros to query for various criteria. We do not recommend using these drop down filters
to query for information, as the results will not format properly. We recommend using the Main Menu to specify
the search criteria. To utilize the drop down filters see AutoFilter and custom AutoFilter in the Microsoft Excel
help menu.
Note:
If the steps selected in the Main Menu do not query and display properly, manually reset all the drop down
filters on the category sheets to 'all'. Go back to the Main Menu and requery for all products.
4. Time limit for steps
The total time for any individual step cannot calculate to more than 23 hours and 59 minutes, due to MS Excel
limitations. When calculating time, Excel will do the following:
|  | Start time |  | End time | Total time
|  | ------------------ |  | ------------------ | --------------
|  | 3/1/00 14:00 |  | 3/2/00 13:59 | 23:59
|  | 3/1/00 14:00 |  | 3/2/00 14:00 | 0:00
|  | 3/1/00 14:00 |  | 3/2/00 14:01 | 0:01
For any single step that requires more than 23 hours and 59 minutes, the time should be entered directly into the
respective Total Time cell.
To Main Page
Return to Top

## Index (hidden)
1 pre-upgrade | Database Upgrade Steps | 10.7 | db
2 pre-upgrade | Applications Technology Products | 11.0 | atg
3 pre-upgrade | Financials Product Family | All Releases | fin
AutoUpgrade | Country-specific Financials Product Family |  | loc
4 post-upgrade | HRMS Product Family |  | hr
5 post-upgrade | Manufacturing and Distribution Product Family |  | man
6 post-upgrade | Public Sector Product Family |  | ps
Custom | All Products |  | all
Do not use the Red cells below.
|  |  | Estimated time | [7 empty] | Crucial Downtime |  |  | Total Time
|  |  | hours | minutes | [6 empty] | hours | minutes |  | hours | minutes
|  | Category 1 | 0 | 0 | 0:00 | [5 empty] | 0 | 0 | 0:00 | 0 | 0 | 0:00
|  | Category 2 | 0 | 0 | 0:00
|  | Category 3 | 0 | 0 | 0:00 | Category 3 | 0 | 0 | 0:00
|  | AutoUpgrade | 0 | 0 | 0:00 | AutoUpgrade | 0 | 0 | 0:00
|  | Category 4 | 0 | 0 | 0:00 | Category 4 | 0 | 0 | 0:00
|  | Category 5 | 0 | 0 | 0:00 | Category 5 | 0 | 0 | 0:00
|  | Category 6 | 0 | 0 | 0:00
|  | Custom | 0 | 0 | 0:00
|  |  | 0 | 0 |  | Total | 0 | 0 |  | Total
|  |  |  | 0 |  | minutes to hour |  | 0 |  | minutes to hour
|  |  | 0 |  |  | add h to hours | 0 |  |  | add h to hours
|  |  |  | 0 |  | convert to time |  | 0 |  | convert to time
|  |  | 0 | 0 | 0:00 | Total hour and minutes | 0 | 0 | 0:00 | Total hour and minutes
|  | AutoUpgrade | 0 | 0 | 0:00
Downtime
|  |  | Actual Time | [7 empty] | Crucial Downtime |  |  | Total Time
|  |  | hours | minutes | [6 empty] | hours | minutes |  | hours | minutes
|  | Category 1 | 0 | 0 | 0:00 | [5 empty] | 0 | 0 | 0:00 | 0 | 0 | 0:00
|  | Category 2 | 0 | 0 | 0:00
|  | Category 3 | 0 | 0 | 0:00 | Category 3 | 0 | 0 | 0:00
|  | AutoUpgrade | 0 | 0 | 0:00 | AutoUpgrade | 0 | 0 | 0:00
|  | Category 4 | 0 | 0 | 0:00 | Category 4 | 0 | 0 | 0:00
|  | Category 5 | 0 | 0 | 0:00 | Category 5 | 0 | 0 | 0:00
|  | Category 6 | 0 | 0 | 0:00
|  | Custom | 0 | 0 | 0:00
|  |  | 0 | 0 |  | Total | 0 | 0 |  | Total
|  |  |  | 0 |  | minutes to hour |  | 0 |  | minutes to hour
|  |  | 0 |  |  | add h to hours | 0 |  |  | add h to hours
|  |  |  | 0 |  | convert to time |  | 0 |  | convert to time
|  |  | 0 | 0 | 0:00 | Total hour and minutes | 0 | 0 | 0:00 | Total hour and minutes
|  | AutoUpgrade | 0 | 0 | 0:00
Downtime

## main_form (hidden)
Main Menu
OK
Cancel
Select a Category, the Product Family, and the Release you are upgrading from for the upgrade steps you want to perform.
Category:
Product Family:
Release: